## CAP-Dashboard
Objective | Action | Deliverable | Deliverable status according to plan | Progress (%) | Milestones | Milestone status according to plan
Objective-2_Communicate to the public, policy makers, and legislators around the world the importance of mitigating GHG emissions to polar bear conservation
0 | CCC-A4: Post and maintain key information related to the Climate Change Communications Strategy on the Polar Bear Range States website.
|  | D1. Climate Change Communications webpage on the PBRS website: A webpage on the Polar Bear Range States website containing the five key messages of the Climate Change Communications Strategy. Each of the individual messages associated with the key messages are also listed. | -0.5 | 50% | M1. Basic website has been fully published: A webpage on the Polar Bear Range States website containing the five key messages of the Climate Change Communications Strategy has been published. | 3
|  | D2. Examples of polar bear conservation and management: Examples of polar bear conservation and management that pertain to each of the five key messages of the Climate Change Communications Strategy, and website links where they exist, are posted on the Polar Bear Range States website as they become available. | -0.2 | 10% | M2. Examples have been acquired and selected: Examples of polar bear conservation and management that pertain to the five key messages have been acquired and selected for sharing using different communication forums. | 3
|  |  | 0 | 0% | M3. Examples have been communicated: Stories/presentations with the selected examples of polar bear conservation and management pertaining to the five key messages are posted on the Polar Bear Range States website, and other communication forums. | 3
|  |  | 0 | 0% |  | 2
|  |  | 0 |  |  | 2
0 | CCC-A5 - Enter into climate change communications partnerships with organizations that have targeted audiences and strong public reach
|  | D1. A report detailing high-level overview of CCC partnership: A report detailing a high-level overview of the climate change communication partnerships that the Range States have entered with external organizations, and what those partnerships entail. | -0.7 | 30% | M1. Report on partnerships been has presented to HoD: Report to be completed when partnership outreach is completed (Spring 2024?) | 2
|  | D2. An assessment of the partnerships and the activities: An assessment of the partnership and the climate change communication activities carried out through them, considering their success and effectiveness in terms of strengthening the climate change communication efforts. | -0.15 | 10% | M2. Assessment of partnerships has been presented to HoD: Assessment to be written before Meeting of Parties (fall Q3 2025?) | 2
|  |  | 0 | 0% |  | 2
|  |  | 0 |  |  | 2
0 | CCC- A6 - Communicate key messages to the public.
|  | D1. A report detailing the events, conferences, special days, and other opportunities: A report detailing the events, conferences, special days, and other opportunities during which the five key messages of the Climate Change Communications Strategy were shared, and a list of which specific messages were shared. | -0.45 | 5% | M1.Communications report has been presented to HoD: Reporting the events, conferences, special days, and other opportunities where comms on the five key messages were shared will happen annually after Q2 | 2
2
2
Objective-3 Ensure the conservation of essential habitat for polar bears
0 | EH – A2 - Define levels of protective status of polar bear essential (or commonly used) habitat (i.e., winter, summer and denning habitat).
|  | D1. For each of the 19 polar bear subpopulations, a map showing the location of protected areas and the essential/commonly used polar bear winter, summer and denning habitats that were identified by the PBSG during the CAP 2020-23 Implementation Period. | -0.15 | 15% | M1. The definition of a protected area has been determined. | 2
|  | D2. A report outlining the methods used to produce the maps. | 0 | 0% | M2. Layers of protected areas have been acquired for as many subpopulations as possible. | 2
|  | D3. Inclusion of Indigenous knowledge in map production | -0.15 | 5% |  | 2
|  |  | 0 | 0% |  | 2
Objective-4 Ensure that harvest of polar bear subpopulations is managed in a biologically sustainable manner in accordance with sound conservation practices
0 | HM – A4 - Submit a description of the harvest regime for each subpopulation
|  | D1. Report with descriptions of the harvest management regimes for all subpopulations | 0 | 0% | M1. Draft report completed and shared for domestic review | 2
[5 empty] | M2. Final report completed and presented on the Range States website | 2
2
0 | HM – A6 - Develop methods to collate available data from harvested bears and how to analyze that data
|  | D1. Report with recommendations for harvest data collection and how harvested bears can inform subpopulation status. | 0 | 0% | M1. Draft white paper with reccomendations completed and shared for domestic review | 2
[5 empty] | M2. White paper completed and published on Range States website | 2
2
Objective-5 Manage human-bear interactions to ensure human safety and to minimize polar bear injury or mortality
0 | HBC – A5 - Report findings on human-bear conflicts which end in injury or death (to bears or humans) annually on the RS website for each country or subpopulation
|  | D1. Table that is published on the Range States website with the number bears injured or killed during conflict situations in 2023. | 0 | 100% | M1. Annual reporting for 2023 completed - website updated | 1
|  | D2. Table that is published on the Range States website with the number bears injured or killed during conflict situations in 2024. | 0 | 0% | M2. Annual reporting for 2024 completed - website updated | 2
|  | D3. Table that is published on the Range States website with the number humans injured or killed during conflict situations in 2023. | 0 | 100%
|  | D4. Table that is published on the Range States website with the number humans injured or killed during conflict situations in 2024. | 0 | 0%
0 | HBC – A8 - Develop Template for site specific conflict mitigation plans
|  | D1. Template of site-specific conflict management plan | 0 | 33% | M1. Develop a draft template | 1
|  |  | 0 | 0% | M2. Range States review draft template | 2
Info tips:
Klick on the arrows to reach the source site
The colour and direction of the arrows indicate the overall status of the deliverable according to workplan.
Green/up: on track
Yellow/horizontal or tilting: at modest risk
Red/down: at great risk
Info tips:
Klick on the icons to reach the source site
The colour and icons indicate the status of the milestone:
Green V: completed
Yellow ! : not completed, pre due date
Red X: not completed, past due date
Info tips:
Proportion of work completed

## Objective Performance Metrics
Objective | Measure of effectiveness/ Impact | Performance Metrics/Indicators | Baseline in 2020 * | Status in March 2022 * | Status in October 2023 * | Expected status in October 2025 *
Objective-2_Communicate to the public, policy makers, and legislators around the world the importance of mitigating GHG emissions to polar bear conservation
| 1. There is an increased awareness in the general public — both locally and globally — about the impacts of climate change on polar bears, due to insights and information provided by the Range States as it relates to their cooperation on polar bear conservation. | Indicator: Traffic to the PBRS website | Numbers of visitors to the RS website in April 2021: 387 visitors 117 direct visitors (29.9%) 270 via search engines (70.1%) | Numbers of visitors to the RS website in April 2022: 3636 visitors 718 direct visitors (19.7%) 2918 via search engines (80.3%) | Once the Climate Change Communications Strategy has been posted on the PBRS website in June 2022, it is likely that traffic to the PBRS website will increase. | It is anticipated that the work associated with CCC-A4, CCC-A5 and CCC-A6 during the 2023-2025 CAP Implementation Period will result in increased traffic to the PBRS website.
| 2. Increase awareness among decision makers about the impacts of climate change on polar bears, due to insights and information provided by the Range States as it relates to their cooperation on polar bear conservation. | Indicator: Survey sent to decision makers and stakeholders | Preliminary idea to measure a baseline: A survey sent to decision makers to gauge their level of awareness of the impacts of climate change on polar bears. Could ask where they get their information on the impacts of climate change on polar bears. |  | Once the Climate Change Communications Strategy has been posted to the PBRS website, and the key messages in the Strategy have been shared in different fora, it is anticipated that decision makers will have an increased awareness of the impacts of climate change on polar bears. | As the PBRS enters into partnerships with external organizations, and as the key messages of the Strategy are communicated during the 2023 – 2025 Implementation Period, it is anticipated that decision makers will have an increased awareness of the impacts of climate change on polar bears.
| 3. Misinformation regarding the impacts of climate change on polar bears among the public, policy makers, and legislators is reduced. | Indicator: Survey sent to decision makers and stakeholders | Preliminary idea to measure a baseline: A survey sent to decision makers to gauge their level of awareness of the impacts of climate change on polar bears. Could ask where they get their information on the impacts of climate change on polar bears. |  | One of the goals of the Climate Change Communications Strategy is to dispel misinformation regarding climate change (e.g., climate change impacts Arctic wildlife only, not people living in the Arctic). Posting the Strategy on the PBRS website and sharing the Strategy’s key messages in different fora will help reach this goal. | It is anticipated that there will be less misinformation regarding climate change and polar bears once this Objective is complete in 2025.
| 4. Number of strategic communication partnerships where climate change communications messages have been developed by Range States and delivered to target audience(s). | Indicator: Number of strategic communication partnerships where climate change communications messages have been developed by Range States and delivered to target audience(s). | When the Range States’ work on climate change communications began, there were no partnerships between the Range States and external organizations that were specifically geared towards climate change communications. |  | The external organizations that were members of the Climate Change Communications Working Group have begun to share the key messages of the Climate Change Communications Strategy. | The external organizations that were members of the Climate Change Communications Working Group have continued to share the key messages of the Climate Change Communications Strategy.
Objective-3 Ensure the conservation of essential habitat for polar bears
| 1. Relative to the baseline essential habitat inventory, changes in the amount of essential habitat in each category as identified by the PBSG (i.e. feeding habitat, mating habitat, denning habitat, migration corridors, and terrestrial refugia) (PBSG). | 1) Changes in the amount of essential habitat in each of the categories of habitat | Baseline needs to be defined. One option for a baseline is the identification of where both protected and unprotected essential habitat currently exists. | The categories of essential habitat are being defined. Work to determine changes in the amount of essential habitat in each category will begin after the categories have been defined, likely during the 2023 – 2025 CAP Implementation Period. | The categories of essential habitat will be defined. Work to determine changes in the amount of essential habitat in each category can begin once the categories have been defined, likely during the 2023 – 2025 CAP Implementation Period.
| 2. Relative to the baseline value, changes in the amount of essential habitat in each of the conservation status categories (PBRS). | 2) Changes in the amount of essential habitat in each of categories of conservation status | Baseline needs to be defined. One option for a baseline is how much essential habitat currently exists in areas with different conservation statuses. | Not started. Work on EH-A2 will commence during the 2023 – 2025 CAP Implementation Period. | Not started. Work on EH-A2 will commence during the 2023 – 2025 CAP Implementation Period.
3. Circumpolar objective: Essential polar bear habitat is consistently described and tracked over time/better understanding/more clarity at the circumpolar level so that each RS can do their job better.
Objective-4 Ensure that harvest of polar bear subpopulations is managed in a biologically sustainable manner in accordance with sound conservation practices
| 1. The proportion of subpopulations where harvest levels are biologically sustainable. | 1) The proportion of subpopulations with harvest which have a quantitative assessment of the population, including accounting for associated uncertainty. | N/A | Postponed until 2023-2025 | Framework for assessment to be complete; assessment to be performed as part of HM-A4, A5, and A6 (2023-2025) | Complete
| 2. The proportion of subpopulations where a demonstrated harvest management regime exists. | 2) The proportion of subpopulations with harvest where harvest data and associated uncertainty is available. | N/A | Postponed until 2023-2025 | Framework for assessment to be complete; assessment to be performed as part of HM-A4, A5, and A6 (2023-2025) | Complete
|  | 3) The proportion of subpopulations with harvest where harvest is determined to be biologically sustainable based on a quantitative assessment. | N/A | Postponed until 2023-2025 | Framework for assessment to be complete; assessment to be performed as part of HM-A4, A5, and A6 (2023-2025) | Will be completed after 2025
|  | 4) The proportion of subpopulations with harvest where quotas and harvest are within biologically sustainable limits (as defined by performance metric 3). | N/A | Postponed until 2023-2025 | Framework for assessment to be complete; assessment to be performed as part of HM-A4, A5, and A6 (2023-2025) | Will be completed after 2025
3. Circumpolar objective: Clarity in terms and consistency in evaluation of harvest across subpopulations and development of methods used to analyze samples collected from harvested bears
Objective-5 Manage human-bear interactions to ensure human safety and to minimize polar bear injury or mortality
| Change in the number of bears injured or killed in conflict situations and in the number of humans injured or killed by bears, compared to the baseline. | 1) Number of bears injured or killed in conflict situations. | 58 (see PBRS website) | Not available yet | Numbers for 2022 will be available
|  | 2) Number of humans injured or killed in conflict situations. | 3 (see PBRS website for record 2016-2020) | Not available yet | Numbers for 2022 will be available
|  | 3) Number of human-bear conflicts resolved without injury or death (i.e., successful use of nonlethal deterrents). | No data | No data | No data
Objective-6 Ensure that international trade of polar bears is carried out according to conservation principles
| International trade is carried out in compliance with CITES. Decrease in the number of CITES violations. No increase in the number of poaching incidents. Increase in the proportion of recommendations from the TWG that have been implemented by all 5 Range States. | 1. Number of subpopulations that have received non-detriment findings by CITES. | In 2020, Canada had an overall positive NDF for polar bear, however, individual export permits were assessed on a case-by-case basis. | As of March 2022, Canada has an overall positive NDF for polar bear, however, individual export permits are assessed on a case-by-case basis. | Canada’s CITES Scientific Authority is currently preparing a Canada-wide NDF Report. This report will be released in mid-2022.
Objective-7 Carry out coordinated circumpolar population research and monitoring to monitor progress toward achieving the vision of the CAP
| To be defined | To be defined | To be defined
*) Baseline and status of Objective performance indicators as defined in column C

## O2-CCC-A4
Objective | Objective Lead
Objective-2_Communicate to the public, policy makers, and legislators around the world the importance of mitigating GHG emissions to polar bear conservation | Lauren Schmuck (Canada)
Action | Action lead(s)
CCC-A4: Post and maintain key information related to the Climate Change Communications Strategy on the Polar Bear Range States website. | Lauren Schmuck (Canada)
|  |  |  | Deliverables - Planned Progress (accumulated %) |  |  |  | Deliverables - Actual Progress (accumulated %)
Deliverables | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status | Progress | Notes of clarification | Needs of HoD action or amendment
D1. Climate Change Communications webpage on the PBRS website: A webpage on the Polar Bear Range States website containing the five key messages of the Climate Change Communications Strategy. Each of the individual messages associated with the key messages are also listed. | Lauren Schmuck (Canada) | 10% | 100% |  |  |  |  | 10% | 50% |  |  |  | -0.5 | 50% | A draft Climate Change Communications website has been developed, and key and individual messages have beena added. The website is very bare and needs additional material added to it. The website has not yet been shared with the members of the CCCWG.
D2. Examples of polar bear conservation and management: Examples of polar bear conservation and management that pertain to each of the five key messages of the Climate Change Communications Strategy, and website links where they exist, are posted on the Polar Bear Range States website as they become available. | Lauren Schmuck (Canada) | 0% | 30% | 75% | 100% |  |  | 0% | 10% |  |  |  | -0.2 | 10% | Prior to the end of the P3 - 4 period, members of the CCCWG will have been asked to share examples of stories of polar bear conservation and management that relate to each of the five key messages, and in particular, any examples that their organizations have been involved in.
0
0
|  |  |  | Milestones - Planned due periods |  |  |  | Milestone status - completed: "yes"/ "no"
Milestones | Contacts | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 |  | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Status |  | Notes of clarification | Needs of HoD action or amendment
M1. Basic website has been fully published: A webpage on the Polar Bear Range States website containing the five key messages of the Climate Change Communications Strategy has been published. | Lauren Schmuck (Canada) |  | x |  |  |  |  | no | no |  |  |  | 3 |  | M1 is partially completed, as of August 2024. Full completion is anticipated during P7-8.
M2. Examples have been acquired and selected: Examples of polar bear conservation and management that pertain to the five key messages have been acquired and selected for sharing using different communication forums. | Lauren Schmuck (Canada) |  | x |  |  |  |  | no | no |  |  |  | 3 |  | M2 will be partially completed, as of the end of the P3 - 4 period. Full completion is anticipated during P7-8.
M3. Examples have been communicated: Stories/presentations with the selected examples of polar bear conservation and management pertaining to the five key messages are posted on the Polar Bear Range States website, and other communication forums. | Lauren Schmuck (Canada) |  | x |  |  |  |  | no | no |  |  |  | 3 |  | M3 will be partially completed, as of the end of the P3 - 4 period. Full completion is anticipated during P7-8.
2
2
|  |  |  | Planned Budget | [5 empty] | Actual Budget
Budget |  | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | Status | Notes of clarification | Needs of HoD action or amendment
Cost other than salary (USD) - PBRS (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - External partners (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - Not secured | [6 empty] | 0 | [5 empty] | 0 | 0%
Tolal cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Planned Working Effort | [5 empty] | Actual Working Effort
Working Effort |  | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | Status | Notes of clarification | Needs of HoD action or amendment
Working effort (hours) - PBRS (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Working effort (hours) - External partners (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Total effort (hours) - (In kind) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Info tips:
Planned progress, due periods, budget and working effort
Planned amounts inserted at the planning phase and after amendments of the Action plan
Responsibilty: Action lead
Info tips:
Actual progress, due periods, budget and working effort
Actual status inserted as needed and no later than at the end of Periods 2, 4, 6, and 8
Responsibilty: Action lead
Info tips:
Colour codes and icons:
The colour of cells and icons indicate the overall status according to the Action plan.
Deliverables:
(>90% of planned progress) : on track
(80-90% of pl. progr.) : at modest risk
(<80% of pl. progr.) : at great risk
Milestones:
: Not completed - pre due date
: Completed
: Not completed - past due date
Info tips:
Periods: division of the 2023-2025 Implementation Plan into 3 months period intvervals
P1-2: Nov. 23 - Apr. 24 P3-4: May. 24- Oct. 24 P5-6: Nov. 24 - Apr. 25 P7-8: May. 25 - Oct. 25
!

## O2-CCC-A5
Objective | Objective Lead
Objective-2_Communicate to the public, policy makers, and legislators around the world the importance of mitigating GHG emissions to polar bear conservation | Lauren Schmuck (Canada)
Action | Action lead(s)
CCC-A5 - Enter into climate change communications partnerships with organizations that have targeted audiences and strong public reach | Lauren Schmuck (Canada)
|  |  |  | Deliverables - Planned Progress (accumulated %) |  |  |  | Deliverables - Actual Progress (accumulated %)
Deliverables | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status | Progress | Notes of clarification | Needs of HoD action or amendment
D1. A report detailing high-level overview of CCC partnership: A report detailing a high-level overview of the climate change communication partnerships that the Range States have entered with external organizations, and what those partnerships entail. | Lauren Schmuck (Canada) | 25% | 100% |  |  |  |  | 15% | 30% |  |  |  | -0.7 | 30% | Parternships have been reformed for the CAP 2023 - 2025 period, between the Polar Bear Range States and the external organizations that compose the Climate Change Communications Working Group.
D2. An assessment of the partnerships and the activities: An assessment of the partnership and the climate change communication activities carried out through them, considering their success and effectiveness in terms of strengthening the climate change communication efforts. | Lauren Schmuck (Canada) |  | 25% | 75% | 100% |  |  | 0% | 10% |  |  |  | -0.15 | 10% | Parternships have been reformed for the CAP 2023 - 2025 period, between the Polar Bear Range States and the external organizations that compose the Climate Change Communications Working Group. Plans for the first meeting of the CCCWG for the CAP 2023 - 2025 period are underway, and the intention is to meet in September (or October) 2024.
0
|  |  |  | Milestones - Planned due periods |  |  |  | Milestone status - completed: "yes"/ "no"
Milestones | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status |  | Notes of clarification | Needs of HoD action or amendment
M1. Report on partnerships been has presented to HoD: Report to be completed when partnership outreach is completed (Spring 2024?) | Lauren Schmuck (Canada) |  | x | [9 empty] | 2
M2. Assessment of partnerships has been presented to HoD: Assessment to be written before Meeting of Parties (fall Q3 2025?) | Lauren Schmuck (Canada) |  |  |  | x | [7 empty] | 2
2
2
|  |  |  | Planned Budget | [5 empty] | Actual Budget
Budget |  | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | Status | Notes of clarification | Needs of HoD action or amendment
Cost other than salary (USD) - PBRS (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - External partners (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - Not secured | [6 empty] | 0 | [5 empty] | 0 | 0%
Tolal cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Planned Working Effort | [5 empty] | Actual Working Effort
Working Effort |  | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | Status | Notes of clarification | Needs of HoD action or amendment
Working effort (hours) - PBRS (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Working effort (hours) - External partners (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Total effort (hours) - (In kind) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Info tips:
Planned progress, due periods, budget and working effort
Planned amounts inserted at the planning phase and after amendments of the Action plan
Responsibilty: Action lead
Info tips:
Actual progress, due periods, budget and working effort
Actual status inserted as needed and no later than at the end of Periods 2, 4, 6, and 8
Responsibilty: Action lead
Info tips:
Periods: division of the 2023-2025 Implementation Plan into 3 months period intvervals
P1-2: Nov. 23 - Apr. 24 P3-4: May. 24- Oct. 24 P5-6: Nov. 24 - Apr. 25 P7-8: May. 25 - Oct. 25
Info tips:
Colour codes and icons:
The colour of cells and icons indicate the overall status according to the Action plan.
Deliverables:
(>90% of planned progress) : on track
(80-90% of pl. progr.) : at modest risk
(<80% of pl. progr.) : at great risk
Milestones:
: Not completed - pre due date
: Completed
: Not completed - past due date

## O2-CCC-A6
Objective | Objective Lead
Objective-2_Communicate to the public, policy makers, and legislators around the world the importance of mitigating GHG emissions to polar bear conservation | Lauren Schmuck (Canada)
Action | Action lead(s)
CCC- A6 - Communicate key messages to the public. | Lauren Schmuck (Canada)
|  |  |  | Deliverables - Planned Progress (accumulated %) |  |  |  | Deliverables - Actual Progress (accumulated %)
Deliverables | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status | Progress | Notes of clarification | Needs of HoD action or amendment
D1. A report detailing the events, conferences, special days, and other opportunities: A report detailing the events, conferences, special days, and other opportunities during which the five key messages of the Climate Change Communications Strategy were shared, and a list of which specific messages were shared. | Lauren Schmuck (Canada) |  | 50% |  | 100% |  |  | 5% | 5% |  |  |  | -0.45 | 5% | The five key messages were presented during the PBRS Meeting of the Parties on October 30 - November 2, 2024. This will be captured in the report. Other opportunities to share the five key messages will be brainstormed, and put into action, during P5, P6, P7, and P8.
|  |  |  | Milestones - Planned due periods |  |  |  | Milestone status - completed: "yes"/ "no"
Milestones | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status |  | Notes of clarification | Needs of HoD action or amendment
M1.Communications report has been presented to HoD: Reporting the events, conferences, special days, and other opportunities where comms on the five key messages were shared will happen annually after Q2 | Lauren Schmuck (Canada) |  |  |  | x |  |  | no | no |  |  |  | 2
2
2
|  |  |  | Planned Budget | [5 empty] | Actual Budget
Budget |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | Status | Notes of clarification | Needs of HoD action or amendment
Cost other than salary (USD) - PBRS (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - External partners (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - Not secured | [6 empty] | 0 | [5 empty] | 0 | 0%
Tolal cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Planned Working Effort | [5 empty] | Actual Working Effort
Working Effort |  | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | Status | Notes of clarification | Needs of HoD action or amendment
Working effort (hours) - PBRS (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Working effort (hours) - External partners (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Total effort (hours) - (In kind) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Info tips:
Planned progress, due periods, budget and working effort
Planned amounts inserted at the planning phase and after amendments of the Action plan
Responsibilty: Action lead
Info tips:
Actual progress, due periods, budget and working effort
Actual status inserted as needed and no later than at the end of Periods 2, 4, 6, and 8
Responsibilty: Action lead
Info tips:
Periods: division of the 2023-2025 Implementation Plan into 3 months period intvervals
P1-2: Nov. 23 - Apr. 24 P3-4: May. 24- Oct. 24 P5-6: Nov. 24 - Apr. 25 P7-8: May. 25 - Oct. 25
Info tips:
Colour codes and icons:
The colour of cells and icons indicate the overall status according to the Action plan.
Deliverables:
(>90% of planned progress) : on track
(80-90% of pl. progr.) : at modest risk
(<80% of pl. progr.) : at great risk
Milestones:
: Not completed - pre due date
: Completed
: Not completed - past due date

## O3-EH-A2
Objective | Objective Lead
Obj. 3 Ensure the conservation of essential habitat for polar bears | Canada (Lauren Schmuck) and Greenland (TBD)
Action | Action lead(s)
EH – A2 - Define levels of protective status of polar bear essential (or commonly used) habitat (i.e., winter, summer and denning habitat). | Canada (Lauren Schmuck) and Greenland (TBD) in cooperation with the PBSG
|  |  |  | Deliverables - Planned Progress (accumulated %) |  |  |  | Deliverables - Actual Progress (accumulated %)
Deliverables | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status | Progress | Notes of clarification | Needs of HoD action or amendment
D1. For each of the 19 polar bear subpopulations, a map showing the location of protected areas and the essential/commonly used polar bear winter, summer and denning habitats that were identified by the PBSG during the CAP 2020-23 Implementation Period. | Lauren Schmuck | 0% | 30% | 60% | 100% |  |  | 5% | 15% |  |  |  | -0.15 | 15% | Correspondence was sent to the PBSG, and a response was received, in P1 and P2. There are some funding issues that need to be discussed before this can advance.
D2. A report outlining the methods used to produce the maps. | Lauren Schmuck | 0% | 0% | 0% | 100% |  |  | 0% | 0% |  |  |  | 0 | 0% | This will be prepared by the PBSG, prior to the PBRS Meeting of the Parties in fall 2025.
D3. Inclusion of Indigenous knowledge in map production | Lauren Schmuck | 0% | 20% | 60% | 100% |  |  | 5% | 5% |  |  |  | -0.15 | 5% | A representative of Inuit Circumpolar Council (ICC) has agreed to participate on the Objective 3 Working Group. This will help ensure Indigenous knowledge is captured in the maps that will be produced.
[13 empty] | 0 | 0%
|  |  |  | Milestones - Planned due periods |  |  |  | Milestone status - completed: "yes"/ "no"
Milestones | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status |  | Notes of clarification | Needs of HoD action or amendment
M1. The definition of a protected area has been determined. |  |  |  | x |  |  |  | no | no |  |  |  | 2 |  | Canada has a definition of "protected area". This will be further discussed with other Range States, and a definition that is agreed upon by all will be reached.
M2. Layers of protected areas have been acquired for as many subpopulations as possible. |  |  |  | x |  |  |  | no | no |  |  |  | 2 |  | It is possible that it will be very challenging to acquire layers of protected areas for all 19 subpopulations.
2
2
|  |  |  | Planned Budget | [5 empty] | Actual Budget
Budget |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | Status | Notes of clarification | Needs of HoD action or amendment
Cost other than salary (USD) - PBRS (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - External partners (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - Not secured | [6 empty] | 0 | [5 empty] | 0 | 0%
Tolal cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Planned Working Effort | [5 empty] | Actual Working Effort
Working Effort |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | Status | Notes of clarification | Needs of HoD action or amendment
Working effort (hours) - PBRS (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Working effort (hours) - External partners (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Total effort (hours) - (In kind) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Info tips:
Planned progress, due periods, budget and working effort
Planned amounts inserted at the planning phase and after amendments of the Action plan
Responsibilty: Action lead
Info tips:
Actual progress, due periods, budget and working effort
Actual status inserted as needed and no later than at the end of Periods 2, 4, 6, and 8
Responsibilty: Action lead
Info tips:
Periods: division of the 2023-2025 Implementation Plan into 3 months period intvervals
P1-2: Nov. 23 - Apr. 24 P3-4: May. 24- Oct. 24 P5-6: Nov. 24 - Apr. 25 P7-8: May. 25 - Oct. 25
Info tips:
Colour codes and icons:
The colour of cells and icons indicate the overall status according to the Action plan.
Deliverables:
(>90% of planned progress) : on track
(80-90% of pl. progr.) : at modest risk
(<80% of pl. progr.) : at great risk
Milestones:
: Not completed - pre due date
: Completed
: Not completed - past due date

## O4-HM-A4
Objective | Objective Lead
Obj. 4 Ensure that harvest of polar bear subpopulations is managed in a biologically sustainable manner in accordance with sound conservation practices | Caroline Ladanowski, Dave Gustine [Alice Garrett July 19, 2024]
Action | Action lead(s)
HM – A4 - Submit a description of the harvest regime for each subpopulation | Caroline Ladanowski
|  |  |  | Deliverables - Planned Progress (accumulated %) |  |  |  | Deliverables - Actual Progress (accumulated %)
Deliverables | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status | Progress | Notes of clarification | Needs of HoD action or amendment
D1. Report with descriptions of the harvest management regimes for all subpopulations | Melissa Galicia and Erik Andersen | 0% | 25% | 75% | 100% |  |  | 0% |  |  |  |  | 0 | 0% | The Operating Team is on track to meet planned progress and next update provided at the end of P3-4. | N/A
[13 empty] | 0 | 0%
[13 empty] | 0 | 0%
[13 empty] | 0 | 0%
|  |  |  | Milestones - Planned due periods |  |  |  | Milestone status - completed: "yes"/ "no"
Milestones | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status |  | Notes of clarification | Needs of HoD action or amendment
M1. Draft report completed and shared for domestic review | Melissa Galicia and Erik Andersen |  | x | x | [8 empty] | 2 |  | The Operating Team is on track to meet milestones status and next update provided at the end of P3-4.
M2. Final report completed and presented on the Range States website | Melissa Galicia and Erik Andersen |  |  |  | x | [7 empty] | 2 |  | The Operating Team is on track to meet milestones status and next update provided at the end of P7-8. | Review the final report for approval
2
2
|  |  |  | Planned Budget | [5 empty] | Actual Budget
Budget |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | Status | Notes of clarification | Needs of HoD action or amendment
Cost other than salary (USD) - PBRS (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - External partners (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - Not secured | [6 empty] | 0 | [5 empty] | 0 | 0%
Tolal cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Planned Working Effort | [5 empty] | Actual Working Effort
Working Effort |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | Status | Notes of clarification | Needs of HoD action or amendment
Working effort (hours) - PBRS (In kind) |  | 10 | 40 | 20 | 5 |  | 75 | 5 |  |  |  |  | 5 | 6.667%
Working effort (hours) - External partners (In kind) |  |  | 10 | 10 |  |  | 20 | [5 empty] | 0 | 0%
Total effort (hours) - (In kind) |  | 10 | 50 | 30 | 5 | 0 | 95 | 5 | 0 | 0 | 0 | 0 | 5 | 5.263%
Info tips:
Planned progress, due periods, budget and working effort
Planned amounts inserted at the planning phase and after amendments of the Action plan
Responsibilty: Action lead
Info tips:
Actual progress, due periods, budget and working effort
Actual status inserted as needed and no later than at the end of Periods 2, 4, 6, and 8
Responsibilty: Action lead
Info tips:
The periods in the plan are the quarter years of the CAP Implementation period
(October 2020 to March 2023):
Q1-2: Oct. 20 - Mar. 21 Q3-4: Apr. 21- Sep. 21 Q5-6: Oct. 21 - Mar. 22 Q7-8: Apr. 22 - Sep. 22
Q9-10: Oct. 22 - Mar. 23
Info tips:
Periods: division of the 2023-2025 Implementation Plan into 3 months period intvervals
P1-2: Nov. 23 - Apr. 24 P3-4: May. 24- Oct. 24 P5-6: Nov. 24 - Apr. 25 P7-8: May. 25 - Oct. 25
Info tips:
Colour codes and icons:
The colour of cells and icons indicate the overall status according to the Action plan.
Deliverables:
(>90% of planned progress) : on track
(80-90% of pl. progr.) : at modest risk
(<80% of pl. progr.) : at great risk
Milestones:
: Not completed - pre due date
: Completed
: Not completed - past due date

## O4-HM-A6
Objective | Objective Lead
Obj. 4 Ensure that harvest of polar bear subpopulations is managed in a biologically sustainable manner in accordance with sound conservation practices | Caroline Ladanowski, Dave Gustine [Alice Garrett July 19, 2024]
Action | Action lead(s)
HM – A6 - Develop methods to collate available data from harvested bears and how to analyze that data | Dave Gustine [Alice Garrett July 19, 2024]
|  |  |  | Deliverables - Planned Progress (accumulated %) |  |  |  | Deliverables - Actual Progress (accumulated %)
Deliverables | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status | Progress | Notes of clarification | Needs of HoD action or amendment
D1. Report with recommendations for harvest data collection and how harvested bears can inform subpopulation status. | Melissa Galicia and Erik Andersen | 0% | 25% | 50% | 100% |  |  | 0% |  |  |  |  | 0 | 0% | The Operating Team is on track to meet planned progress and next update provided at the end of P3-4. | N/A
[13 empty] | 0 | 0%
[13 empty] | 0 | 0%
[13 empty] | 0 | 0%
|  |  |  | Milestones - Planned due periods |  |  |  | Milestone status - completed: "yes"/ "no"
Milestones | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status |  | Notes of clarification | Needs of HoD action or amendment
M1. Draft white paper with reccomendations completed and shared for domestic review | Melissa Galicia and Erik Andersen |  | x | x | [8 empty] | 2 |  | The Operating Team is on track to meet milestones status and next update provided at the end of P3-4. | N/A
M2. White paper completed and published on Range States website |  |  |  |  | x | [7 empty] | 2 |  | The Operating Team is on track to meet milestones status and next update provided at the end of P7-8. | Review the final report for approval
2
2
|  |  |  | Planned Budget | [5 empty] | Actual Budget
Budget |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | Status | Notes of clarification | Needs of HoD action or amendment
Cost other than salary (USD) - PBRS (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - External partners (granted) |  | 4406 | 0 | 0 | 2500 |  | 6906 | [5 empty] | 0 | 0% | Financial resources for the activities relating the achievement of Deliverable D1 continue to be provided by Canada during the CAP2023-2025 in form of an independent contract with Dr. Eric Regehr at the University of Washington.
Cost other than salary (USD) - Not secured | [6 empty] | 0 | [5 empty] | 0 | 0%
Tolal cost |  | 4406 | 0 | 0 | 2500 | 0 | 6906 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Planned Working Effort | [5 empty] | Actual Working Effort
Working Effort |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | Status | Notes of clarification | Needs of HoD action or amendment
Working effort (hours) - PBRS (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Working effort (hours) - External partners (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Total effort (hours) - (In kind) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Info tips:
Planned progress, due periods, budget and working effort
Planned amounts inserted at the planning phase and after amendments of the Action plan
Responsibilty: Action lead
Info tips:
Actual progress, due periods, budget and working effort
Actual status inserted as needed and no later than at the end of Periods 2, 4, 6, and 8
Responsibilty: Action lead
Info tips:
Periods: division of the 2023-2025 Implementation Plan into 3 months period intvervals
P1-2: Nov. 23 - Apr. 24 P3-4: May. 24- Oct. 24 P5-6: Nov. 24 - Apr. 25 P7-8: May. 25 - Oct. 25
Info tips:
Colour codes and icons:
The colour of cells and icons indicate the overall status according to the Action plan.
Deliverables:
(>90% of planned progress) : on track
(80-90% of pl. progr.) : at modest risk
(<80% of pl. progr.) : at great risk
Milestones:
: Not completed - pre due date
: Completed
: Not completed - past due date

## O5-HBC-A5
Objective | Objective Lead
Obj. 5 Manage human-bear interactions to ensure human safety and to minimize polar bear injury or mortality | TBD
Action | Action lead(s)
HBC – A5 - Report findings on human-bear conflicts which end in injury or death (to bears or humans) annually on the RS website for each country or subpopulation | TBD
|  |  |  | Deliverables - Planned Progress (accumulated %) |  |  |  | Deliverables - Actual Progress (accumulated %)
Deliverables | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status | Progress | Notes of clarification | Needs of HoD action or amendment
D1. Table that is published on the Range States website with the number bears injured or killed during conflict situations in 2023. | Droplaug Ólafsdóttir |  | 100% |  |  |  |  | 80.1% | 100% |  |  |  | 0 | 100%
D2. Table that is published on the Range States website with the number bears injured or killed during conflict situations in 2024. | Droplaug Ólafsdóttir |  |  |  | 100% | [7 empty] | 0 | 0%
D3. Table that is published on the Range States website with the number humans injured or killed during conflict situations in 2023. | Droplaug Ólafsdóttir |  | 100% |  |  |  |  | 80% | 100% |  |  |  | 0 | 100%
D4. Table that is published on the Range States website with the number humans injured or killed during conflict situations in 2024. | Droplaug Ólafsdóttir |  |  |  | 100% | [7 empty] | 0 | 0%
|  |  |  | Milestones - Planned due periods |  |  |  | Milestone status - completed: "yes"/ "no"
Milestones | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status |  | Notes of clarification | Needs of HoD action or amendment
M1. Annual reporting for 2023 completed - website updated | Droplaug Ólafsdóttir |  | x |  |  |  |  | no | yes |  |  |  | 1
M2. Annual reporting for 2024 completed - website updated | Droplaug Ólafsdóttir |  |  |  | x |  |  | no | no |  |  |  | 2
2
2
|  |  |  | Planned Budget | [5 empty] | Actual Budget
Budget |  | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | Status | Notes of clarification | Needs of HoD action or amendment
Cost other than salary (USD) - PBRS (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - External partners (granted) | [6 empty] | 0 | [5 empty] | 0 | 0%
Cost other than salary (USD) - Not secured | [6 empty] | 0 | [5 empty] | 0 | 0%
Tolal cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Planned Working Effort | [5 empty] | Actual Working Effort
Working Effort |  | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | P1-2 | P3-4 | P5-6 | P7-8 | P9-10 | Total | Status | Notes of clarification | Needs of HoD action or amendment
Working effort (hours) - PBRS (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Working effort (hours) - External partners (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Total effort (hours) - (In kind) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Info tips:
Planned progress, due periods, budget and working effort
Planned amounts inserted at the planning phase and after amendments of the Action plan
Responsibilty: Action lead
Info tips:
Actual progress, due periods, budget and working effort
Actual status inserted as needed and no later than at the end of Periods 2, 4, 6, and 8
Responsibilty: Action lead
Info tips:
The periods in the plan are the quarter years of the CAP Implementation period
(October 2020 to March 2023):
Q1-2: Oct. 20 - Mar. 21 Q3-4: Apr. 21- Sep. 21 Q5-6: Oct. 21 - Mar. 22 Q7-8: Apr. 22 - Sep. 22
Q9-10: Oct. 22 - Mar. 23
Info tips:
Periods: division of the 2023-2025 Implementation Plan into 3 months period intvervals
P1-2: Nov. 23 - Apr. 24 P3-4: May. 24- Oct. 24 P5-6: Nov. 24 - Apr. 25 P7-8: May. 25 - Oct. 25
Info tips:
Colour codes and icons:
The colour of cells and icons indicate the overall status according to the Action plan.
Deliverables:
(>90% of planned progress) : on track
(80-90% of pl. progr.) : at modest risk
(<80% of pl. progr.) : at great risk
Milestones:
: Not completed - pre due date
: Completed
: Not completed - past due date

## O5-HBC-A8
Objective | Objective Lead
Obj. 5 Manage human-bear interactions to ensure human safety and to minimize polar bear injury or mortality | TBD
Action | Action lead(s)
HBC – A8 - Develop Template for site specific conflict mitigation plans | Dave Gustine
|  |  |  | Deliverables - Planned Progress (accumulated %) |  |  |  | Deliverables - Actual Progress (accumulated %)
Deliverables | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status | Progress | Notes of clarification | Needs of HoD action or amendment
D1. Template of site-specific conflict management plan |  |  | 33% | 66% | 100% |  |  |  | 33% |  |  |  | 0 | 33%
[13 empty] | 0 | 0%
[13 empty] | 0 | 0%
[13 empty] | 0 | 0%
|  |  |  | Milestones - Planned due periods |  |  |  | Milestone status - completed: "yes"/ "no"
Milestones | Contacts | P1-2 | P3-4 | P5-6 | P7-8 |  |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Status |  | Notes of clarification | Needs of HoD action or amendment
M1. Develop a draft template |  |  | x | [5 empty] | yes |  |  |  | 1
M2. Range States review draft template |  |  |  | x | [8 empty] | 2
M3. Final template |  |  |  |  | x | [7 empty] | 2
2
|  |  |  | Planned Budget | [5 empty] | Actual Budget
Budget |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | Status | Notes of clarification | Needs of HoD action or amendment
Cost other than salary (USD) - PBRS (granted) |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | 0 | 0%
Cost other than salary (USD) - External partners (granted) |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | 0 | 0%
Cost other than salary (USD) - Not secured |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | 0 | 0%
Tolal cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  |  | Planned Working Effort | [5 empty] | Actual Working Effort
Working Effort |  | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | P1-2 | P3-4 | P5-6 | P7-8 |  | Total | Status | Notes of clarification | Needs of HoD action or amendment
Working effort (hours) - PBRS (In kind) | [6 empty] | 0 | 80 |  |  |  |  | 80 | 0%
Working effort (hours) - External partners (In kind) | [6 empty] | 0 | [5 empty] | 0 | 0%
Total effort (hours) - (In kind) |  | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 80 | 0%
Info tips:
Planned progress, due periods, budget and working effort
Planned amounts inserted at the planning phase and after amendments of the Action plan
Responsibilty: Action lead
Info tips:
Actual progress, due periods, budget and working effort
Actual status inserted as needed and no later than at the end of Periods 2, 4, 6, and 8
Responsibilty: Action lead
Info tips:
The periods in the plan are the quarter years of the CAP Implementation period
(October 2020 to March 2023):
Q1-2: Oct. 20 - Mar. 21 Q3-4: Apr. 21- Sep. 21 Q5-6: Oct. 21 - Mar. 22 Q7-8: Apr. 22 - Sep. 22
Q9-10: Oct. 22 - Mar. 23
Info tips:
Periods: division of the 2023-2025 Implementation Plan into 3 months period intvervals
P1-2: Nov. 23 - Apr. 24 P3-4: May. 24- Oct. 24 P5-6: Nov. 24 - Apr. 25 P7-8: May. 25 - Oct. 25
Info tips:
Colour codes and icons:
The colour of cells and icons indicate the overall status according to the Action plan.
Deliverables:
(>90% of planned progress) : on track
(80-90% of pl. progr.) : at modest risk
(<80% of pl. progr.) : at great risk
Milestones:
: Not completed - pre due date
: Completed
: Not completed - past due date

## progress-codes (hidden)
Progress | Due period
yes | x
no